## Launch Schedule & Checklist
For more information about successful medical device launch planning and execution, please read the eBook which can be downloaded here:
Create a new product launch schedule in this worksheet. Enter title of this launch in cell B2. Information about how to use this worksheet, including instructions for screen readers and the author of this workbook is in the instructions & information tab. Continue navigating down column A to see additional instructions. | NEW DEVICE LAUNCH TITLE | https://www.definitivehc.com/resources/ebooks/medical-device-strategy-cross-functional-guide
Enter Company Name in cell B3. | Company Name
Enter the name of the Launch Lead in cell B4. Enter the Project Start date in cell F4. Project Start: label is in cell E4. | Launch Lead Name | Project Start: |  |  | 2022-04-19
The Display Week in cell F5 represents the starting week to display in the project schedule in cell J5. The project start date is considered Week 1. To change the display week, simply enter a new week number in cell F5. The starting date for each week, starting with the display week from cell F5, starts in cell J5 and is auto calculated. You should not modify these cells. Display Week: label is in cell D5. |  | Display Week: |  |  | 1 |  |  | 2022-04-18 | [6 empty] | 2022-04-25 | [6 empty] | 2022-05-02 | [6 empty] | 2022-05-09 | [6 empty] | 2022-05-16 | [6 empty] | 2022-05-23 | [6 empty] | 2022-05-30 | [6 empty] | 2022-06-06 | [6 empty] | 2022-06-13 | [6 empty] | 2022-06-20 | [6 empty] | 2022-06-27 | [6 empty] | 2022-07-04 | [6 empty] | 2022-07-11 | [6 empty] | 2022-07-18 | [6 empty] | 2022-07-25 | [6 empty] | 2022-08-01 | [6 empty] | 2022-08-08 | [6 empty] | 2022-08-15 | [6 empty] | 2022-08-22 | [6 empty] | 2022-08-29 | [6 empty] | 2022-09-05 | [6 empty] | 2022-09-12 | [6 empty] | 2022-09-19 | [6 empty] | 2022-09-26 | [6 empty] | 2022-10-03 | [6 empty] | 2022-10-10 | [6 empty] | 2022-10-17 | [6 empty] | 2022-10-24 | [6 empty] | 2022-10-31 | [6 empty] | 2022-11-07 | [6 empty] | 2022-11-14 | [6 empty] | 2022-11-21 | [6 empty] | 2022-11-28 | [6 empty] | 2022-12-05 | [6 empty] | 2022-12-12 | [6 empty] | 2022-12-19 | [6 empty] | 2022-12-26 | [6 empty] | 2023-01-02 | [6 empty] | 2023-01-09 | [6 empty] | 2023-01-16 | [6 empty] | 2023-01-23
Cells J5 through KJ5 contain the day number for the week represented in the cell block above each date cell and are auto calculated. You should not modify these cells. Today's date is outlined in Red (hex #AD3815) from today's date in row 6 through the entire date column to the end of the project schedule. | time axis 2022-04-18 to 2023-01-29
This row contains headers for the project schedule that follows below them. Navigate from B7 through KJ7 to hear the content. The first letter of each day of the week for the date above that heading, starts in cell J7 and continues through cell KJ7. All project timeline charting is auto generated based on the start and end dates entered, using conditional formats. Do not modify content in cells within columns after column J starting with cell J8. | TASK | ASSIGNED TO | TASK DURATION (DAYS) | PROGRESS | START | END | DAYS | time axis 2022-04-18 to 2023-01-29
Do not delete this row. This row is hidden to preserve a formula that is used to highlight the current day within the project schedule.
Cell B9 contains the marketing function. Modify as needed in cell B9. Enter a name to assign this phase to, if it applies for your project, in cell C9. Enter the estimated duration of this functions tasks in cell D9. Enter Progress for the entire phase, if it applies for your project, in cell D9. Enter the start and end dates for the entire phase, if it applies for your project, in cells E9 and F9. The Gantt chart will automatically fill in the appropriate dates and shade according to the progress entered. To delete the phase and work only from tasks, simply delete this row. | Marketing
Cell B9 contains the sample task "Task 1." Enter a new task name in cell B9. Enter a person to assign the task to in cell C9. Enter estimated duration in days to cell D9 Enter progress of the task in cell E9. A progress bar appears in the cell and is shaded according to the number in the cell. For example, 50 percent progress would shade half of the cell. Enter task start date in cell F9. Task end date will automatically populate based on the task duration entered. A status bar shaded for the dates entered appears in blocks starting from cell I9 through BL9. | Identify key competitors and create objection handling, competitive counter-detailing | Name | 5 | 75% | 2022-04-19 | 2022-04-24 | 6
Rows 10 through 13 repeat the pattern from row 9. Repeat the instructions from cell A9 for all task rows in this worksheet. Overwrite any sample data. A sample of another phase starts in cell A14. Continue entering tasks in cells A10 through A13 or go to cell A14 to learn more. | Identify target audience & target market(s) in conjunction with sales |  | 2 | 60% | 2022-04-24 | 2022-04-26 | 3
| Market segmentation in conjunction with sales |  | 2 | 50% | 2022-04-26 | 2022-04-28 | 3
| Identify buyer personas along with challenges & solutions sought |  | 2 | 35% | 2022-04-28 | 2022-04-30 | 3
| Define value proposition and differentiators - Do differentiators vary based on market segment? |  | 2 | 35% | 2022-04-30 | 2022-05-02 | 3
Cell B9 contains the sample task "Task 1." Enter a new task name in cell B9. Enter a person to assign the task to in cell C9. Enter progress of the task in cell D9. A progress bar appears in the cell and is shaded according to the number in the cell. For example, 50 percent progress would shade half of the cell. Enter task start date in cell E9. Enter task end date in cell F9. A status bar shaded for the dates entered appears in blocks starting from cell I9 through BL9. | Define messaging, features, and benefits - Does messaging vary based on market segment? | Name | 2 | 75% | 2022-05-02 | 2022-05-04 | 3
Rows 10 through 13 repeat the pattern from row 9. Repeat the instructions from cell A9 for all task rows in this worksheet. Overwrite any sample data. A sample of another phase starts in cell A14. Continue entering tasks in cells A10 through A13 or go to cell A14 to learn more. | Work in conjunction with sales to understand target buying process - Including where they buy (e.g. distribution channels) - Is there a value analysis committee? |  | 2 | 60% | 2022-05-04 | 2022-05-06 | 3
| Marketing material development (utilize clinical trial and other outcome data points in conjunction with MA) Reminder, you cannot market your device until after FDA clearance/approval and registration |  | 2 | 50% | 2022-05-06 | 2022-05-08 | 3
| Work in conjunction with finance and contract marketing to develop pricing strategy - Including potential tier strategy for varying commitment/volume levels - GPO or individual agreement pricing strategy |  | 60 | 20% | 2022-05-08 | 2022-07-07 | 61
| Develop training content materials in conjunction with sales training |  | 2 | 35% | 2022-07-07 | 2022-07-09 | 3
Cell B9 contains the sample task "Task 1." Enter a new task name in cell B9. Enter a person to assign the task to in cell C9. Enter progress of the task in cell D9. A progress bar appears in the cell and is shaded according to the number in the cell. For example, 50 percent progress would shade half of the cell. Enter task start date in cell E9. Enter task end date in cell F9. A status bar shaded for the dates entered appears in blocks starting from cell I9 through BL9. | Budget planning | Name | 2 | 75% | 2022-07-09 | 2022-07-11 | 3
Rows 10 through 13 repeat the pattern from row 9. Repeat the instructions from cell A9 for all task rows in this worksheet. Overwrite any sample data. A sample of another phase starts in cell A14. Continue entering tasks in cells A10 through A13 or go to cell A14 to learn more. | Website strategy. Including content development, landing pages to convert traffic to leads, premium content, and implementation. Execute and strategize in conjunction with agency or internal department as applicable |  | 2 | 60% | 2022-07-11 | 2022-07-13 | 3
| Generate campaign strategy within budget restrictions in conjunction with marketing communications for awareness building and lead generation. Execute on marketing plan. Considerations: - Advertising & Promotion (including industry publications, societies, conferences) - Social media - Email marketing -Thought leadership content - Webinars - Print publications |  | 2 | 50% | 2022-07-13 | 2022-07-15 | 3
| Determine conference presence and engage KOLs for speaking engagements to support launch |  | 2 | 30% | 2022-07-15 | 2022-07-17 | 3
| Submit marketing/promotional materials for Medical/legal/regulatory review |  | 2 | 30% | 2022-07-17 | 2022-07-19 | 3
The cell at right contains the sales function. You can create a new phase at any time within column B. This project schedule does not require phases. To remove the phase, simply delete the row. To create a new phase block in this row, enter a new Title in cell at right. To continue adding tasks to the phase above, enter a new row above this one and fill in the task data as in cell A9's instruction. Update the Phase details in cell at right based on cell A8's instruction. Continue navigating down column A cells to learn more. If you haven't added any new rows in this worksheet, you will find 2 additional sample phase blocks have been created for you in cells B20 and B26. Otherwise, navigate through column A cells to find the additional blocks. Repeat the instructions from cells A8 and A9 whenever you need to. | Sales
| Identify target market(s) in conjunction with marketing | Name | 2 | 50% | 2022-05-01 | 2022-05-03 | 3
| Market segmentation in conjunction with marketing |  | 4 | 50% | 2022-05-03 | 2022-05-07 | 5
| Territory alignment |  | 3 | 5% | 2022-05-05 | 2022-05-08 | 4
| Sales leadership to determine target accounts in conjunction with marketing |  | 1 | 50% | 2022-05-07 | 2022-05-08 | 2
| Work in conjunction with marketing to understand target buying process | Name | 2 | 50% | 2022-05-09 | 2022-05-11 | 3
| Determine sales process for new device |  | 3 | 50% | 2022-05-11 | 2022-05-14 | 4
| Determine staffing needs and onboard sales personnel |  | 5 | 5% | 2022-05-13 | 2022-05-18 | 6
| Create target account listing with potential dollar value broken out by sales territory & market segment |  | 10 | 50% | 2022-05-15 | 2022-05-25 | 11
| Attend product and competitor training and ensure proficiency |  | 2 | 50% | 2022-05-17 | 2022-05-19 | 3
| Research target accounts to determine pre-call planning and outreach strategy |  | 1 | 5% | 2022-05-19 | 2022-05-20 | 2
| Identify GPO relationships with target accounts |  | 4 | 50% | 2022-05-21 | 2022-05-25 | 5
| Develop customer onboarding and implementation plan: -How will you ensure customers have success with your new device? -In conjunction with medical affairs and marketing, determine inservicing needs to be prepared for the first customer sale Reminder: you cannot sell your device until after FDA clearance/approval and registration | Name | 2 | 50% | 2022-05-23 | 2022-05-25 | 3
Sales Ops/Business analytics function block | Sales Operations / Business Analytics
| Identify target market(s) | Name | 2 | 50% | 2022-05-04 | 2022-05-06 | 3
| Market segmentation |  | 3 | 50% | 2022-05-07 | 2022-05-10 | 4
| Build territory alignment based on market and account research with sales leadership direction |  | 1 | 5% | 2022-05-12 | 2022-05-13 | 2
| Develop target account criteria with sales leadership and perform analysis for account identification |  | 5 | 50% | 2022-05-14 | 2022-05-19 | 6
| Determine sales process for new device and develop tracking/monitoring mechanism | Name | 2 | 50% | 2022-05-13 | 2022-05-15 | 3
| Create target account listing with potential dollar value broken out by sales territory & market segment | Name | 3 | 50% | 2022-05-15 | 2022-05-18 | 4
| Research target accounts to assist sales with pre-call planning and outreach strategy |  | 4 | 50% | 2022-05-19 | 2022-05-23 | 5
| Evaluate and select CRM vendor > set up and maintain CRM |  | 2 | 5% | 2022-05-24 | 2022-05-26 | 3
| Work with marketing to build lead generation and lead communication mechanism |  | 2 | 50% | 2022-05-27 | 2022-05-29 | 3
| Develop mechanism for win/loss analysis tracking |  | 2 | 50% | 2022-05-30 | 2022-06-01 | 3
Sales training function block | Sales Training
| Determine sales training deployment mechanism: -In-person/on-site sales training -Live virtual sales training -Use of eLearning platform | Name | 2 | 50% | 2022-06-02 | 2022-06-04 | 3
| Identify training topics in conjunction with marketing: -Market segments -Messaging -Available tools and collateral -Buyer personas -Buying process -Selling practices |  | 2 | 50% | 2022-06-05 | 2022-06-07 | 3
Contracting function block | Contracting
| Submit new device within GPO award cycle to ensure inclusion on GPO listing; if off-cycle understand with GPO's if new product can be added | Name | 2 | 50% | 2022-05-19 | 2022-05-21 | 3
| Research and develop reimbursement strategy to determine most common payers |  | 1 | 50% | 2022-05-22 | 2022-05-23 | 2
| Work with identified payer organizations to understand how to include your device included and what data is required to prove clinical and economic value |  | 2 | 5% | 2022-05-27 | 2022-05-29 | 3
| Finalize and implement reimbursement strategy |  | 4 | 50% | 2022-05-29 | 2022-06-02 | 5
| Set up distributor chargeback process (if applicable) | Name | 10 | 50% | 2022-05-28 | 2022-06-07 | 11
| Evaluate and select contract management and compliance tracking system |  |  | 50% | 2022-05-30 | 2022-05-30 | 1
| Work in conjunction with marketing on pricing strategy - including potential tier strategy for varying commitment/volume levels - GPO or individual agreement pricing strategy - WAC & list pricing |  | 60 | 25% | 2022-05-08 | 2022-07-07 | 61
| Develop internal processes for processing chargebacks, implementing pricing strategy, tracking contract memberships to GPO, IDN, and/or physician groups, monitoring contract compliance monitoring and executing rebate requirements. |  |  | 25% | 2022-06-08 | 2022-06-08 | 1
Market access & HEOR function block | Market Access / HEOR
| Perform an initial assessment to identify relevant payors to include in your reimbursement strategy. (Delineate between CMS and commercial payors) | Name | 45 | 8% | 2022-04-19 | 2022-06-03 | 46
| Understand payor approval processes |  | 60 | 50% | 2022-06-04 | 2022-08-03 | 61
| Investigate code development: -Why is a need code needed? -Why does your organization want a new code? -Is there a significant difference in the product or technique? |  | 10 | 5% | 2022-06-09 | 2022-06-19 | 11
| Determine code development process if there is substantial reason and differentiation. |  | 60 | 50% | 2022-06-20 | 2022-08-19 | 61
| Tee up clinical evidence generation with R&D, regulatory and medical to meet both FDA requirements and payor requirements. |  | 365 | 5% | 2022-06-25 | 2023-06-25 | 366
| Reimbursement amount should also be used to inform pricing strategy with contracting and marketing |  | 45 | 50% | 2023-06-26 | 2023-08-10 | 46
Regulatory function block | Regulatory
| Determine process for complaint submission in conjunction with quality | Name | 60 | 50% | 2022-06-03 | 2022-08-02 | 61
| Establish CAPA procedure in conjunction with quality and manufacturing operations for investigating product complaints and implementing correction or corrective actions |  | 60 | 50% | 2022-08-03 | 2022-10-02 | 61
| New organizations: Identify and map process for issuing product recalls in conjunction with manufacturing, site quality, and corporate quality |  | 60 | 5% | 2022-08-08 | 2022-10-07 | 61
| Post 510(k) clearance or PMA, complete product registration |  | 60 | 50% | 2022-10-08 | 2022-12-07 | 61
| Review marketing materials for clinical claims & supporting evidence |  | 30 | 50% | 2022-08-08 | 2022-09-07 | 31
Corporate quality function block | Corporate Quality
| Determine process for complaint submission in conjunction with regulatory. Consider how: -Clients will report complaints -The complaint is logged, reviewed, and routed for investigation -Mechanism for return of product in question | Name | 45 | 50% | 2022-05-04 | 2022-06-18 | 46
| Establish CAPA procedure in conjunction with regulatory, site quality, and manufacturing operations for investigating product complaints and implementing corrections or corrective actions |  | 30 | 50% | 2022-06-19 | 2022-07-19 | 31
| New organizations: Identify and map process for issuing product recalls in conjunction with manufacturing, site quality, and regulatory |  | 15 | 5% | 2022-06-24 | 2022-07-09 | 16
Site quality function block | Site Quality
| Finalize design transfer with R&D/program management and manufacturing operations, including development and documentation of auditing protocols | Name | 25 | 50% | 2022-06-18 | 2022-07-13 | 26
| Establish CAPA procedure in conjunction with corporate quality and manufacturing operations, and regulatory for investigating product complaints and implementing corrections or corrective actions |  | 18 | 50% | 2022-07-14 | 2022-08-01 | 19
| New organizations: Identify and map QMS process for issuing product recalls in conjunction with regulatory and corporate quality |  | 60 | 5% | 2022-07-19 | 2022-09-17 | 61
Medical affairs function block | Medical Affairs
| Closely align with HEOR or market access to ensure that all clinical evidence is gathered and available for reimbursement strategy | Name | 180 | 5% | 2022-04-19 | 2022-10-16 | 181
| Identify and engage KOLs for clinical support as needed for reimbursement strategy |  | 60 | 50% | 2022-10-17 | 2022-12-16 | 61
| Work in conjunction with marketing on clinical claims within marketing materials |  | 30 | 5% | 2022-10-22 | 2022-11-21 | 31
| Set up internal process for answering off-label inquiries |  | 60 | 50% | 2022-11-22 | 2023-01-21 | 61
| Review marketing materials for clinical claims & supporting evidence | Name | 30 | 50% | 2022-07-03 | 2022-08-02 | 31
| Work with marketing to determine conference presence and engage KOLs for speaking engagements to support launch |  | 60 | 50% | 2022-08-03 | 2022-10-02 | 61
| Develop customer onboarding and implementation plan: -How will you ensure customers have success with your new device? -In conjunction with sales and customer experience, determine inservicing needs to be prepared for the first customer sale |  | 30 | 5% | 2022-08-08 | 2022-09-07 | 31
Trading partner management function block | Trading Partner Management
| Work in conjunction with marketing to determine distribution strategy – where/how do targets typically buy? | Name | 30 | 50% | 2022-07-03 | 2022-08-02 | 31
| HDA form completion for med-surg distributor or wholesaler set up |  | 30 | 50% | 2022-08-03 | 2022-09-02 | 31
| Work in conjunction with contract marketing on setting up the distributor chargeback contract and process |  | 30 | 5% | 2022-08-08 | 2022-09-07 | 31
Supply chain/Logistics function block | Supply Chain / Logistics
| Develop supply chain and logistics strategy: -Third part logistics (3PL) -Distributors -Owned distribution/warehousing -Proprietary fleet | Name | 15 | 50% | 2022-05-04 | 2022-05-19 | 16
| If owned warehousing, how will product be distributed? -Owned fleet -Shipping service -Freight company |  | 30 | 8% | 2022-05-20 | 2022-06-19 | 31
| Deployment planning -Determine timing, quantity, and where product will be shipped for distribution |  | 10 | 10% | 2022-05-25 | 2022-06-04 | 11
| Demand planning / forecasting: -Before your first sale, you need to make forecasting assumptions to determine production schedule and the volume of your first lot to stock -This can be done using market data and company determined growth targets and should be done in conjunction with marketing -Develop future forecasting cycle and accuracy tracking, to have in place after the new device is launched |  | 20 | 25% | 2022-06-05 | 2022-06-25 | 21
IT/ERP management function block | IT / ERP Management
| Set up order management system with new product number, product description, EDI ordering, ERP management | Name | 10 | 50% | 2022-07-18 | 2022-07-28 | 11
| Conduct order placement testing |  | 8 | 50% | 2022-07-29 | 2022-08-06 | 9
| Releasing controls for deployment, order placement and shipment after FDA approval and registration in conjunction with marketing and regulatory |  | 5 | 5% | 2022-08-03 | 2022-08-08 | 6
R&D Program management function block | R&D / Program Management
| Finalize design transfer per FDA 21 CFR Part 820 |  | 120 | 10% | 2022-04-19 | 2022-08-17 | 121
| Align closely with market access/HEOR and medical affairs to understand clinical evidence gathering requirements for reimbursement strategy | Name | 120 | 10% | 2022-04-19 | 2022-08-17 | 121
Customer experience function block | Customer Experience
| New customer onboarding | Name | 10 | 15% | 2022-08-02 | 2022-08-12 | 11
| Customer service support: -Will there be a dedicated team for your new device? -Will there be a direct point of contact for each customer? -Will there be customer support by geographical region? -Will customer support be aligned to sales territory? |  | 20 | 20% | 2022-08-13 | 2022-09-02 | 21
| What kind of customer communications will the team handle? (Ensure there is a documented process and that the team is trained) -Product enhancements -Supply disruptions -New releases -Updates |  | 15 | 5% | 2022-08-18 | 2022-09-02 | 16

## Instructions & Information
About This Template
This excel template provides a simple way to create a Gantt chart for those unfamiliar with Microsoft Project. This template helps to visualize and track all of your new product launch project deliverables across the organization. This has been pre-populated with the tactical tasks that align to the Definitive Healthcare eBook, "Cross-functional guide to medical device launch strategy and execution" which can be downloaded here: Modify the tasks to align with what you have determined are applicable to your medical device organization along with specific start and end dates - no formulas required. The bars in the Gantt chart represent the duration of the task and are displayed using conditional formatting. Insert new tasks by inserting new rows.
Guide for Screen Readers
There are 2 worksheets in this workbook. Launch schedule & checklist Instructions & information The instructions for each worksheet are in the A column starting in cell A1 of each worksheet. They are written with hidden text. Each step guides you through the information in that row. Each subsequent step continues in cell A2, A3, and so on, unless otherwise explicitly directed. For example, instruction text might say "continue to cell A6" for the next step. This hidden text will not print. To remove these instructions from the worksheet, simply delete column A.
About Definitive Healthcare
At Definitive Healthcare, our mission is to transform data, analytics and expertise into healthcare commercial intelligence. We help clients uncover the right markets, opportunities and people, so they can shape tomorrow’s healthcare industry. Our SaaS platform creates new paths to commercial success in the healthcare market, so companies can identify where to go next. Definitive Healthcare provides the most comprehensive healthcare commercial intelligence you need to prepare for every step of the commercialization process and accelerate your go-to-market journey. Our data products, tools and services can assist you with all aspects of planning, strategy and execution. With insights across multiple market perspectives all unified in one single source of truth, you can improve your chances of success. Our solutions for medical device organizations are aligned with the FDA device development process to ensure that you have the greatest chance of success in bringing your device to market and making a positive impact on patient care.